## Timeline
Generic Timeline (Big Events)
|  | Time Prior to Event | Milestone or Task | Comments | Status | Assignee(s) | Notes
| 1 | 12 months | Set Target Date for Event | determine date of event or time frame (to be solidified when venue reservation is made)
| 2 | 11 months | reserve the venue | make "deposit" type of payment for venue if appropriate based on estimated attendance
| 3 | 10 months | Assign Project manager/Event Director, course designer(s)
| 4 | 9 months | Start Advertisement design, Award design, determine classes
| 5 | 8 months | Complete Advertisement design and review, order awards
| 6 | 7 months | Make/update Attackpoint event, send Ads to Orienteering Magazine(s), Alert nearby clubs, local newspapers, etc
| 7 | 6 months | apply for usage permits | applies to cases where the event is spread across many different areas that are controlled by different authorities
8
| 9 | 4 months | Open registration, Review course design, get volunteers
10
| 11 | 4 months | contact naturalist(s) | and review control placement
| 12 | 3 months | finalize permits
| 13 | 3 months | Distribute initial registration list in preparation for for onsite check-in/registration via computer | (software with manual backup)
14
| 15 | 2 months | Complete course design and starting vetting, receive awards
16
| 17 | 1 month | Close registration, distribute list for Software preparation, follow up on ambiguous registrations
| 18 | 2 weeks | Complete vetting, confirm volunteers
| 19 | 1 week | Prepare check-in packets, determine and document schedule for the day of the event, prepare check-in checklist for volunteers | checklist should include re-checking members of each team, signing waviers, re-check assigned class category, re-check finger stick number, recheck cell phone number to be carried if appropriate
20
| 21 | Day of Event: Check-in | setup check-in area, follow checklist for participant check-in, communicate schedule for the day
22
| 23 | Day of Event: Results | setup results area, check off people coming in, periodically check on-going results for errors, give final results to Event Director | make sure everyone is back, leave no one out there
24
| 25 | Ongoing | make periodic contact with venue contact person | to review plan for usage, identify and resolve any conflicts, etc.
NEOOC - v5 - 16-October-2018 - FCM